## Sheet1
Iteration #1 | Feature | Feature | Feature | Feature
Date of milestone
Features in scope | Register Users | REST API relating to the topic of the project | Continous Deployment Pipeline | Authorisation/Security
Features implemented | Register Users | REST API with sample data | Continous Deployment Pipeline | Authorisation/Security
Features in deficit this Iteration
Iteration Comments & Summary | API works seamlessly with the Azure database. | Continous Deployment YAML files written, not currently in | Work will speed up after my IMD CA.
| Security manager mostly implemented. API not secure yet. | the GitHub. | I have a solid base to work with.
| Registration of users works. | Work is slow due to assignments and tests.
Iteration #2 6/12/20 | Feature | Feature | Feature | Feature
Date of milestone
Features in scope | Post API | Image Upload | Profile | Profile Picture
Features implemented | Post API | Mostly done | A little bit done. Having trouble with ASP.Net Identity.
Features in deficit this Iteration | Profile picture not done.
Iteration Comments & Summary | Absolutely horrible due to current college workload. Can feel I can get nothing done. | Authorisation, registering, totally finished. | Feel more adept at adding other APIs because I have one out of the way.
Iteration #3 | Feature | Feature | Feature | Feature
Date of milestone 20/12/20 | Code Quality + Unit Tests | Image Upload Done | Successfully Getting Data from Asp.Net Identity | Profile Still in Development
Features in scope
|  | Worst out of the way for the new year. | Had three assignments due since iteration started
Features in deficit this Iteration |  |  | I am not superman!
Iteration Comments & Summary
Iteration #4 | Feature | Feature | Feature | Feature
Date of milestone 14/02/20
Features in scope | Feed, Viewing Posts on Profile | Following and Liking | Image Upload with Google Cloud | Profile Settings
Features implemented | Feed, Viewing Posts on Profile | Following and Liking | Image Upload with Google Cloud | Profile Settings
Features in deficit this Iteration
Iteration Comments & Summary | Working on Azure deploy more. Worked out serious hurdles with IdentityManager. | Need to start getting to the 'meat' of the project now. | I think things are going fine.
|  | Starting to make it unique. | However, Blazor is very new technology.
Iteration #5 | Feature | Feature | Feature | Feature
Date of milestone 10/03/20
Features in scope | Shopping Cart | Stripe Integration | Beginning Front-End Work | Azure Pipeline
Features implemented | Shopping Cart | Stripe Integration | Beginning Front-End Work | Azure Pipeline
Features in deficit this Iteration
Iteration Comments & Summary | Things are going well.
Iteration #6 | Feature | Feature | Feature | Feature
Date of milestone 30/03/20
Features in scope | Hashtags | Suggestion Algorithms | Analysis Page
Features implemented | Hashtags | Suggestion Algorithms
Features in deficit this Iteration |  |  | Analysis Page
Iteration Comments & Summary | Slow iteration. I think pandemic depression is to blame.
Iteration #7 | Feature | Feature | Feature
Date of milestone 23/04/20
Features in scope | CI/CD Pipeline In Full | Unit Tests/Selenium Tests | Code Quality
Features implemented | CI/CD Pipeline In Full | Unit Tests/Selenium Tests | Code Quality
Features in deficit this Iteration
Iteration Comments & Summary